## Working route
Blackboard Group No ?? Class XYY | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks |  |  |  |  | Version 1 |  |  |  |  | Version 2 (option |  |  |  |  | Version 3 (option) |  |  |  |  | Final Submit (and version 4 option)
SMART goals ==> | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
hide this row after inputting class date |  | class date | =====> | 2021-03-30 |  |  |  | class date plus | 7 | workdays |  |  | class date plus | 12 | workdays |  |  | plus | 17 | workdays | Last possible submit date: | 2021-04-25 | plus | 20 | days
Each team member | Project Mgmt Activity | share with team |  | Wednesday Mar.31 | DONE
Group Meeting Agenda ==> | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Thursday Apr.1 | DONE | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 1.5 | Monday Apr.5 | TO DO | refine plan, update DONE items with actual hours. Version 2: edit artefacts and request review | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1.5 | Monday Apr.12 | TO DO | update plan, Version 2 & 3: revise artefacts and request last review | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1.5 | Monday Apr.19 | TO DO | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. | 1.5 | Thursday Apr.22 | TO DO
[Bilal Albayati] Action Items | Use word processor to Outline ideas and approaches for all aspects of the project and post in the MS Channel | Select Fundamentals Module (Indexing) Download File Project Source Code.zip and review files and and edit CP4P_Final_Assignment_Plan.xslx file Download and Install git | 2 | Thursday Apr.1 | DONE | For (Fundamentals Module, Indexing): Using Visual Studio Code, Review code, comment, compile, unit test using gcc and command line | Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt files to Sheba via MS Teams | 10 | Tuesday Apr.6 | TO DO | For (Fundamentals Module, Measuring): Using Visual Studio Code, Review and enter code, compile, develop and run test cases initialize and configure git repository | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 10 | Tuesday Apr.13 | TO DO | For (Fundamentals Module, Copying): Using Visual Studio Code,, Review and enter code, compile, develop and run test cases | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 10 | Tuesday Apr.20 | TO DO | For (Fundamentals Module, e): Using Visual Studio Code, Review and enter code, compile, develop and run test cases | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 12 | Friday Apr.23 | TO DO
[Sheba Birhanu] Action Items | Use word processor to Outline ideas and approaches for all aspects of the project | Select Manipulations Module (Concatenation) Download File Project Source Code.zip, review files and create CP4P_Final_Assignment_Plan.xslx file to post in MS Teams and and upload Version#.zip to MS Teams Files and request review Download and Install git | 2 | Thursday Apr.1 | DONE | For (Manipulations Modules, Concatenation) Using Visual Studio Code, review code, comment, integrating modules into the main application, compile, unit test and system test using gcc and command line | Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Tuesday Apr.6 | TO DO | For (Manipulations Module, Comparison): Using Visual Studio Code, Review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code initialize and configure git repository | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Tuesday Apr.13 | TO DO | For (Manipulations Module, Search): Using Visual Studio Code,, review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Tuesday Apr.20 | TO DO | For (Manipulations Module, Validation and error handling of any input causing unexpected output): Using Visual Studio Code,, review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 12 | Friday Apr.23 | TO DO