## Working route
Blackboard Group No ?? Class XYY | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks |  |  |  |  | Version 1 |  |  |  |  | Version 2 (option |  |  |  |  | Version 3 (option) |  |  |  |  | Final Submit (and version 4 option)
SMART goals ==> | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | deliverable is Measurable & Agreed upon | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
hide this row after inputting class date |  | class date | =====> | 2021-03-30 |  |  |  | class date plus | 7 | workdays |  |  | class date plus | 12 | workdays |  |  | plus | 17 | workdays | Last possible submit date: | 2021-04-25 | plus | 20 | days
Each team member | Project Mgmt Activity | share with team |  | Wednesday Mar.31 | DONE
Group Meeting Agenda ==> | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Thursday Apr.1 | DONE | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 1.5 | Monday Apr.5 | DONE | refine plan, update DONE items with actual hours. Version 2: edit artefacts and request review | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1.5 | Monday Apr.12 | DONE | update plan, Version 2 & 3: revise artefacts and request last review | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1.5 | Monday Apr.19 | DONE | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. | 1.5 | Thursday Apr.22 | DONE
[Bilal Albayati] Action Items | Use word processor to Outline ideas and approaches for all aspects of the project and post in the MS Channel | Select Fundamentals Module (Indexing) Download File Project Source Code.zip and review files and and edit CP4P_Final_Assignment_Plan.xslx file Download and Install git | 2 | Thursday Apr.1 | DONE | For (Fundamentals Module, Indexing): Using Visual Studio Code, Review code, comment, compile, unit test using gcc and command line | Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt files to Sheba via MS Teams | 10 | Tuesday Apr.6 | DONE WEDNESDAY | For (Fundamentals Module, Measuring): Using Visual Studio Code, Review and enter code, compile, develop and run test cases initialize and configure git repository | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 10 | Tuesday Apr.13 | DONE SATURDAY | For (Fundamentals Module, Copying): Using Visual Studio Code,, Review and enter code, compile, develop and run test cases | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 10 | Sunday April 18th | DONE | For (Fundamentals Module, e): Using Visual Studio Code, Review and enter code, compile, develop and run test cases | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file send .c and .h and .txt and .png files to Sheba via MS Teams | 12 | Friday Apr.23 | DONE
[Sheba Birhanu] Action Items | Use word processor to Outline ideas and approaches for all aspects of the project | Select Manipulations Module (Concatenation) Download File Project Source Code.zip, review files and create CP4P_Final_Assignment_Plan.xslx file to post in MS Teams and and upload Version#.zip to MS Teams Files and request review Download and Install git | 2 | Thursday Apr.1 | DONE | For (Manipulations Modules, Concatenation) Using Visual Studio Code, review code, comment, integrating modules into the main application, compile, unit test and system test using gcc and command line | Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Tuesday Apr.6 | DONE WEDNESDAY | For (Manipulations Module, Comparison): Using Visual Studio Code, Review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code initialize and configure git repository | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Tuesday Apr.13 | DONE WEDNESDAY | For (Manipulations Module, Search): Using Visual Studio Code,, review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 10 | Sunday April 18th | DONE | For (Manipulations Module, Validation and error handling of any input causing unexpected output): Using Visual Studio Code,, review and enter code, compile, develop and run test cases , capture git screenshots unit test and system test all code | Capture git screenshots Run and document the test case results. Capture the console output of your tests and paste into a text file upload Version#.zip to MS Teams Files and submit to blackboard | 12 | Friday Apr.23 | DONE
Note on A2: ====== ID#AAAAL5remSE Tim McKenna (2021-03-30 20:37:06) Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: ====== ID#AAAAL5remTE Tim McKenna (2021-03-30 20:37:06) Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: ====== ID#AAAAL5remS4 Tim McKenna (2021-03-30 20:37:06) This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: ====== ID#AAAAL5remTo Tim McKenna (2021-03-30 20:37:06) How many hours will the task take?
Note on E2: ====== ID#AAAAL5remSg Tim McKenna (2021-03-30 20:37:06) When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: ====== ID#AAAAL5remS8 Tim McKenna (2021-03-30 20:37:06) Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: ====== ID#AAAAL5remTA Tim McKenna (2021-03-30 20:37:06) Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: ====== ID#AAAAL5remSI Tim McKenna (2021-03-30 20:37:06) This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: ====== ID#AAAAL5remTU Tim McKenna (2021-03-30 20:37:06) How many hours will the task take?
Note on J2: ====== ID#AAAAL5remSw Tim McKenna (2021-03-30 20:37:06) When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: ====== ID#AAAAL5remSM Tim McKenna (2021-03-30 20:37:06) Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: ====== ID#AAAAL5remTQ Tim McKenna (2021-03-30 20:37:06) Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: ====== ID#AAAAL5remSQ Tim McKenna (2021-03-30 20:37:06) This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: ====== ID#AAAAL5remTk Tim McKenna (2021-03-30 20:37:06) How many hours will the task take?
Note on O2: ====== ID#AAAAL5remTI Tim McKenna (2021-03-30 20:37:06) When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: ====== ID#AAAAL5remS0 Tim McKenna (2021-03-30 20:37:06) Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: ====== ID#AAAAL5remSU Tim McKenna (2021-03-30 20:37:06) Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: ====== ID#AAAAL5remTM Tim McKenna (2021-03-30 20:37:06) This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: ====== ID#AAAAL5remTg Tim McKenna (2021-03-30 20:37:06) How many hours will the task take?
Note on T2: ====== ID#AAAAL5remSY Tim McKenna (2021-03-30 20:37:06) When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: ====== ID#AAAAL5remSc Tim McKenna (2021-03-30 20:37:06) Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: ====== ID#AAAAL5remSk Tim McKenna (2021-03-30 20:37:06) Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: ====== ID#AAAAL5remSo Tim McKenna (2021-03-30 20:37:06) This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: ====== ID#AAAAL5remSs Tim McKenna (2021-03-30 20:37:06) How many hours will the task take?
Note on Y2: ====== ID#AAAAL5remTc Tim McKenna (2021-03-30 20:37:06) When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: ====== ID#AAAAL5remTY Tim McKenna (2021-03-30 20:37:06) Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.